## Sheet1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Michael Risher			Date	3/9/2016				1. Enter your name, and the date you started the programming assignment.
Program	Sorting Bag			Program #	2				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.

Program Size (LOC)				Actual	Last Program		To Date		Prior to development:
Base (B)			(counted)	127	96				0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	10
Modified (M)			(counted)	118	51				1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	118	55
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	236	106		342
Total LOC (T)			(counted)	245	141		386		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		46.7326732673	20.9900990099		55.9128065395
				After development:
Time in Phase (minutes)			Plan	Actual	Last Program	To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			60	58	2	60	16%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			5		2	2	1%
Code			120	170	50	220	60%
Compile			5		0	0	0%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			60	75	10	85	23%
Postmortem					0	0%
Total			250	303	64	367	100%

Defects Injected				Actual	Last Program	To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0%
Design					0	0%
Code				8	2	10	100%
Compile					0	0%
Test					0	0%		Summary
Postmortem					0	0%		Bag class with selection sort and merge sort
Total Development				8	2	10	100%

Defects Removed				Actual	Last Program	To Date	To Date %
Planning					0	0%
Design					0	0%
Code				8	2	10	100%
Compile					0	0%
Test					0	0%
Postmortem					0	0%
Total Development				8	2	10	100%
After Development				0	0	0

				Michael Risher			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)